## Harweel 2008 HSE Plan Final
HARWEEL PROJECT HSE PLAN 2008 - OSH |  |  | Rev-Final 25/March/2008
S/N | HSEMS Element | TEAM ACTIONS | KEY PERFORMANCE INDICATORS (KPI) | Resp Action Party | Accountable | UNIT | 2008 TGT | Q1 TGT | Q1 ACT | Q2 TGT | Q2 ACT | Q3 TGT | Q3 ACT | Q4 TGT | Q4 ACT | REMARK
1 | Leadership & Commitment | PDO/Harweel Safety Day 1& 2 - Kick off by TLs | Safety Day 1&2 - TLs meeting with MOM recorded | Mgmt-TL's | OSH | Number | 2 |  |  | 1 |  |  |  | 1 |  | Safty dates PDO: early June and probably October.
2 |  | IRC Participation by Team leaders (rotation scheme) and quarterly feedback on IRC learnings to HWL-Team | Each TL attended at least 1 IRC | Mgmt-TL's | OSHH/SHH3 | Number | 8 | 2 |  | 2 |  | 2 |  | 2
3 |  | Monthly Mgmt-site HSE inspections: each Mgmt-TL participates in at least two | Signed Inspection report (Common Standard) | Mgmt-TL's | OSHH/SHH3 | Number | 12 | 3 |  | 3 |  | 3 |  | 3
4 |  | Senior Management engagement with drivers at Site | 1 engament per quarter | Mgmt-TL's | OSHH/SHH3 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
5 |  | Hold Site Contractors HSE Forums | 2 Contractors HSE Forums led by OSH/OSHC - MOM issued | OSH/OSHC | OSH/OSHH | Number | 2 |  |  | 1 |  |  |  | 1
6 | Policies & Strategic Objectives | All Project SITE staff Complete the "Revised Induction Session". This will include a Driving Safely focus, Golden Rules and Goal Zero! Alligned with QA/QC and FSI. | Site training log | Mgmt-TL's | OSHC/OSHH | Number | 100% | 25% |  | 25% |  | 25% |  | 25%
7 | Organisational structure, resources, standards & documentation | Identify HSE critical positions and establish competency gaps of individuals filling these positions | List completed in 4/08, Self assessment completed in Q2, training/development identified Q3. 50% of PDO construction staff, 100% of PDO operations staff, 50% of Engineering staff | OSHC OSHO OSHE | OSHH | % | 100% |  |  | 50% |  | 25%
8 |  | HSE plan actions included in Individual PC & PDP (training) | Signed off staff PC & PDP that include HSE actions in line with this HSE plan | Mgmt-TL's | OSH/OSHH | % | 100% | 75% |  | 25%
9 | HEMP | All Site and Operations PDO Project Staff to complete the STOP for Supervision training package | PDO Staff numbers against recorded attendance | OHHC OSHO | OSHH3 | % | 100% | 25% |  | 25% |  | 25% |  | 25%
10 |  | Construction Activities to have a Code 1 HEMP and JHA as a minimum | HEMP & JHA Code 1 Approved | OSHC/1/2 | OSHH3 | % | 100% | 25% |  | 25% |  | 25% |  | 25%
11 |  | Implementation of theTI framework | Identify SCE's, Performance Standards siigned off and verification scheme defined | OSHI |  | % | 100% |  |  |  |  | 75% |  | 25%
12 |  | Complete operations HSE case | HSE Case signed off by Asset Holder | OSHO/5 | OSH0 | % | 100% |  |  |  |  | 100%
13 | Plan and Procedures | Develop, sign off and track 2008 HSE plan implementation | (1) Signed HSE plan (2) Quarterly status report | Mgmt-TL's | OSHH | Number | 4 | 1 |  | 1 |  | 1 |  | 1
14 |  | All staff complete PDO Safety Day Sessions | Signed attendance sheets | Mgmt-TL's | OSHC/OSHH | % | 100% | 50% |  |  |  | 50%
15 |  | All Harweel site staff has completed a Harweel Driving Peer Review | Signed attendance, review sheet and Training Matrix | Site Mgmt-TL's | OSHH3 | % | 100% | 25% |  | 25% |  | 25% |  | 25%
16 |  | Develop PTW and handover procedures to manage the commision and operations phase of the project | Issue PTW and handover procedures | OSHC OSHO/2 | OSHO | % | 100% |  |  | 50% |  |  |  | 50% |  | PTW Procedure: June. Handover procedures Dec
17 |  | Develop HRA's for all commisioning/operations positions | HRA's issued | OSHO/1/2 |  | % | 100% |  |  |  |  | 50% |  | 50%
18 | Implementation and Monitoring | Develop and implement Health and Welfare activities and monitor/review quarterly. | Health & Welfare review quarterly report | OSHC/1/2 | OSHH3 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
19 |  | Site HSE Action Tracking Review | Quaterly review by OSHC & OSHH: MOM issued | OSHC/H |  | Number | 4 | 1 |  | 1 |  | 1 |  | 1
20 |  | Quarterly review and analysis of HSE lagging and leading indicators | Quarterly report on indicators below and analysis issued | OSHH | OSHH/OSHH3 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
LAGGING INDICATORS: for 2008
|  |  | LTIF: (days without a sign event) |  |  | LTIF | 0.5
|  |  | TRCF (max number of TRC's) |  |  | TRCF | 5
|  |  | TROIF (number of Occ Illnesses) |  |  | TROIF | 0.3
|  |  | RTAF (days without an RTA) |  |  | RTAF | 2
LEADING INDICATORS : for 2008
|  |  | Number of STOP Cards with closed actions |  | OSHH3 | Number | no/month | 200 |  | 200 |  | 200 |  | 200
|  |  | Health Awareness Sessions |  | OSHH3 | Number | 16 | 4 |  | 4 |  | 4 |  | 4
|  |  | Environmental Awareness Sessions |  | OSHH2 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
|  |  | PDO staff Driving Safety Forums (Site and MAF) |  | OSHH3 | Number | 8 | 2 |  | 2 |  | 2 |  | 2
21 | Audit | Develop PDO Contract HSE audit/inspection/monitoring plan (intergated with FSI/QA-QC) | Approved PDO Contract HSE audit/inspection/monitoring plan: to be issued quarterly as function of project activities. | OSHH/3 | OSHH/OSHH3 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
22 |  | Implement PDO Contract HSE audit/inspection/monitoring plan, track audit items and close out recommendations. | Quarterly review of: (1) Audit/inspection/montoring activities held against plan (2) Outstanding Action items | Mgmt-TL's | OSHH3 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
23 |  | External verification of HSEMS applied in Harweel | two Level 2 HSE MS audits: one construction one before start of utilities commisioning by PEC | OSHC OSHO | OSH/OSHH | Number | 2 |  |  | 1 Level 2 |  |  |  | 1 Level 2
24 |  | Monitor compliance with Environmental Specifications | 4 environmental audits | OSHC/H | OSHH2 | Number | 4 | 1 |  | 1 |  | 1 |  | 1
25 |  | Road Safety/Logistics SP-2000 compliance (Road Safety) audits | 2 road safety/logistics audits | OSHC/H | OSHH3 | Number | 2 |  |  | 1 |  |  |  | 1
26 |  | Radiogprahy specification compliance audits | 2 radiography audits | OSHC/H | OSHH3 | Number | 2 | 1 |  |  |  | 1
27 |  | Lifting compliance | 2 lifting audits | OSHC/H | OSHH3 | Number | 2 | 1 |  |  |  | 1
28 |  | PTW and Simops compliance (PDO and PEC systems) | 2 PTW audits | OSHC/H | OSHH3 | Number | 2 |  |  | 1 |  |  |  | 1
29 |  | Monitor and report implementation of HRA's by PEC | 2 HRA audits | OSHC/H | OSHH3 | Number | 2 |  |  | 1 |  |  |  | 1
30 | Management Review | Review status of HSE plan implementation | Quarterly report and MOM of the review meeting plus presentation of highligfhts to HWL-Team. | OSHH | OSH/OSHH | Number | 4 | 1 |  | 1 |  | 1 |  | 1
31 |  | SAQ by Management Team and Section Heads | 1 completed SAQ's | Mgmt-TL's | OSH/OSHH | Number | 1 | [6 empty] | 1
32 |  | Review/evaluate 2008 performance as input to 2009 HSE Plan | Review Meeting held | Mgmt-TL's | OSH/OSHH | Number | 1 | [6 empty] | 1
Author Accepted: Kevin Doyle, Tony van Thiel
Accepted Challenge: MGMT team
Accepted : Project Manager Ian Hill

## Harweel 2007 HSE Plan Q4 Review
HARWEEL PROJECT HSE PLAN 2007 |  |  | Q4 review Mark up: dd 3/Feb/2008 Final
S/N | HSEMS Element | TEAM ACTIONS | KEY PERFORMANCE INDICATORS (KPI) | Action Party | Driven by | UNIT | 2007 TGT | Q1 TGT | Q1 ACT | Q2 TGT | Q2 ACT | Q3 TGT | Q3 ACT | Q4 TGT | Q3/4 ACT | Q1 Status Comment | Q1 Review Action | Q2 Status Comment | Q2 Review Action | Q4 Status Comment | Q4 Review Action
1 | Ensure Leadership & Commitment | All Project staff attend the Golden Rules Session and sign project HSE commitment Statement. | Current Numbers of staff measured against recorded attendance and signed commitment statement | Mgmt-TL's | Tony/Kevin | % | 100% | 80% | 80% | 10% | 90% | 10% |  |  |  | about 80%. 4 Sessions at Site (25), 4 at MAF (70) 1 at Sharjah (30). | Do another 2 sessions in each area in Q2 for new comers and thiose that missed the Q1 sessions. Issue the commitments with short cover not as a reminder of the rules, | Site: Ongoing continuosly Sharjah: most done in Q1 MAF: new staff status not clear | Do another 2 sessions at MAF and Sharjah to clean up for new staff. Records into training Matrix. | New staff were covered by supervisors and group sessions done in Sharjah and site. | For 2008: OSHH to produce one combined Golden Rules/Goal Zero package to be placed on OSH website. Roll out to new staff by supervsiors.
2 |  | MGMT-TL to complete HSE Competence Self Assessment in Q2 | Completed self assessment in CBD tool | Mgmt-TL's | Tony | % | 100% | 50% | 60% | 50% | 75% |  |  |  |  | 5 out of 9 (8 excluding OSHD) Self Assesments completed: OSH, OSHC, OSHE, OSHH, OSHO 3 verified | Tony to issue detials to remaining TL for self assessment. (OSHH - end April) | 6 out of 9 (8 excluding OSHD) Self Assesments completed: OSH, OSHC, OSHE, OSHH, OSHO, OSHQ 4 verified | Tony to issue detials to remaining TL for self assessment. (OSHH - end Sept) | Status: 6 self assements completed and verified. OSHS/OSHD outstanding but not really required. | Complete full assesment of OSHI
3 |  | Monthly Mgmt-site HSE inspections: each Mgmt-TL participates in al least two | Signed Inspection report (Common Standard) | Mgmt-TL's | Kevin | Number | 12 | 3 | 3 | 3 | 10 | 3 |  | 3 | 3 | 3 done (Ernest Tony). One large one diuring site progress meeting. Process now streamlined. | TL to formally plan 1 inspection each in Q2. Advise OSHH/3 when you will do this and request target area. (TL) | All have done 1. Most 2 | TL to formally plan 1 inspection each in Q4. Advise OSHH/3 when you will do this and request target area. (TL) | Al done. Not all in site format. | Repeat Mgmt HSE inspections in 2008
4 | Policies & Strategic Objectives | Apply rewards for excellent HSE performance. | Documented HSE award to PDO or Contractor staff (e.g.: Shukran) | Mgmt-TL's | OSHC | Number | 12 | 3 | 3 | 3 | 9 | 3 |  | 3 | 3 | During the 3 million hrs: 1 Galfar and 1 Tekfen man publicly rewarded. 1 at Coast. | Must be further streamlined. Scheme started on site with handout of raffle type tickets which are used for prices. | Shukrans PDO and Contractor staff issued. | Formal record to be kept | Shukrans to PDO and HSE Incentive awards to Contractor staff issued. | Keep rewarding staff in 2008 but not as part of HSE Plan.
5 |  | Apply sanctions for violations on HSE performance. | Documented action of HSE sanction to PDO or Contractor staff (e.g.: warning letter) | Mgmt-TL's | OSHC | Number | 4 | 1 | ? | 1 |  | 1 |  | 1 | 1 | 2 Warning letters Tekfen. 15 stars removed (14 Galfar, 1 Tekfen) | Document sanctions and star reovals in list and keep uptodate. (OSHH/3) | 23 Warning letters Tekfen. 87 stars removed (14 Galfar, 1 Tekfen) 6 Default Notices |  | 2007 full year: 29 warning letters isuued, 87 stars removed, 4 PDO warning letters, 10 HSE Defaults. In 2 cases people were fired. | Keep staff sanctions and contractor defaults in 2008 but not as part of HSE Plan.
6 | Organisational structure, resources, standards & documentation | Identify HSE critical positions and establish competency gaps of individuals filling these positions | List completed in Q2, Self assessement completed in Q3, training/development identified Q4 | Mgmt-TL's | Tony | % | 100% |  | 0% | 25% | 0% | 50% |  | 25% | 0% | Not formally started. | To be kicked off early May: action OSHH to issue details. | Not formally started. | To be kicked off end Sept: action OSHH to issue details. | Not formally kicked off. OSHO team has made considerable progress. | Included in corporate plan for 2008. Include in OSH/2008 plan
7 |  | HSE plan actions included in Inividual PC & PDP (training) | Signed off staff PC & PDP that include HSE actions in line with this HSE plan | Mgmt-TL's | Ian Hill | % | 100% | 75% | 50% | 25% | [5 empty] | On 4/4 status of PC's was 52%. Not easy to check status of HSE items included. |  | PC's Reviewed 95%: SAP status list |  | Achieved | Continue in 2008 (outside HSE plan ??)
8 |  | Monthly HSE Meeting structure defined and implemented | Structure define in Jan. Issued MOM and action items closed. | Mgmt-TL's | Tony | Number | 12 | 3 | 3 | 3 | 6 | 3 |  | 3 | 3 | Meeting structure defined at site. MAF/Sharjah: included in each progress/coordination meeting. | Formalis TOR for PDO Monthly HSE Meeting in Muscat and Sharjah start process in May (OSHH) | Meeting structure defined at site. MAF/Sharjah: included in each progress/coordination meeting. Started HWL HSE Forum an IRC's |  | Achieved. Meetings and IRC's take place | Review/redefine HSE meeting structure early 2008
9 | HEMP | All PDO Project Staff to (re) complete the STOP for Supervision training package | PDO Staff numbers against recorded attendance | Mgmt-TL's | Akhtar | % | 100% | 50% | 25% | 25% | 75% | 25% |  |  |  | Rescheduled for coast (corporate allignement). Site: 1 month behind schedule. Target site to get the cards going by 1/June replacing current NCR's | Role out stop in Sharjah (action OSHH/1) and Muscat (action OSHO/3) in Q2 | Site: Implemented 85% staff, live in August. MAF: operations team to start | Role out stop in Muscat (action OSHO/3) in Q4 Q1/08 Awarness session in Sharjah | Site: 100% . Sharjah awarness session completed. MAF: move to 2008 (mainly for OSHO staff). | Include STOP in 2008 plan
10 |  | Complete all design HSE requirements as per contract spec | Delivery of doucments IFD/C status | OSHE | Ian Bett | % | 100% | 25% | ?? | 25% |  | 25% |  | 25% | 25% | not sure where we are? | OSHH/1 to extract list of deliverables and advise status plus plane by end May. | not sure where we are? Being tracked as part of Design Deliverables. | OSHH/1 to extract list of deliverables and advise status. | Ongoing as part of design work | None
11 |  | Complete operations HSE case | HSE Case signed off by Asset Holder | OSHH/O | Ian Bett | % | 100% | [6 empty] | 100% | 100% | Plan in place (OSHH/1, OSHE/1, OSHO) |  | Design HSE Case in progress Ops HSE Case moved to 2008 on advise HSEMS audit team |  | Design HSE Case completed. Operations HSE case moved into 2008 on advise HSE-MS audit team | Include Operations HSE case in 2008 plan
12 | Plan and Procedures | Develop, sign off and track 2007 HSE plan implementation | (1) Signed HSE plan (2) Quarterly status report | Mgmt-TL's | Tony | Number | 4 | 1 | 1 | 1 | 2 | 1 |  | 1 | 1 | this process: first review | Issue formal report by en April (OSHH) | this process: second review (late) | Issue formal report by end Sept (OSHH) | 3 out 4 review held | Plan for 3 reviews in 2008?
13 |  | All OSH staff complete PDO and Site HSE induction training | Issued HSE Training passport and site induction records | Mgmt-TL's | Sabrina/Daljit | % | 100% | 25% | 25% | 25% | 50% | 25% |  | 25% |  | Site HSE ionduction: 100% PDO HSE induction: no clear list available | Traing list to be update by all: Tony to prepare note for Ian to send (end April) to HWL staff to update their thraing status in Matrix (mid May) | Site HSE induction: 100% PDO HSE induction as people arrive. Formal Records to be verfied in training matrix for all OSH staff | Traing list to be update by all: Tony to prepare note for Ian to send (end Sept) to HWL staff to update their thraing status in Matrix (mid Oct) | Note not send but all new arrivals get their induction. OSHO team and site teams have accurate training matrix in place. | Update training matrix in 2008 to include MAF and Sharjah staff
14 |  | All OSH staff has attended the DDC/1 Defensive Driving Course | Issued PDO Driving Permit and HSE training records | Mgmt-TL's | Tony | % | 100% | 25% | 25% | 25% | 50% | 25% |  | 25% |  | No staff driving in PDO vehicles without DDC. For private driving ?? | Traing list to be update by all: Tony to prepare note for Ian to send (end April) to HWL staff to update their thraing status in Matrix (mid May) | Work Related : 100% Private driving: not clear overview | See above: Supervisors to ask each staff | All site staff have attended. Most MAF and Sharjah also. Training Matrix to be updated | Update training matrix in 2008 to include MAF and Sharjah staff
15 |  | Monitor managent of all project wastes in line with Environmental Sepcifications | 4 waste management audits | OSHC | Sabrina | Number | 4 | 1 | 0 | 1 | 2 | 1 |  | 1 | 1 | 1 completed in April (2 weeks late) | Next one in Q2. | 2 completed: OK | Next one in Q3/4 | Environmental audit completed in Q3
16 | Implementation and Monitoring | Monitor and report implementation of HRA's by PEC | By Audit Q2 & Q4 | OSHC | Jim | Number | 2 |  |  | 1 |  |  |  | 1 |  | HRA process started on site. | Audit in May June (OSHH/3) | HRA's on file: 25 Specific Audit not done | Going well but formal audit to be completed. | Formal audit not done. Amber (instead of red) justified by a highly active joint PDO/PEC/Galgar/Tekfen health committee | Execute formal Health audit in 2008
17 |  | Monitor SP-2000 compliance (Road Safety) through audit | 4 road safety/logistics audits | OSHC | Zahran | Number | 4 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 started in April (1 month late) | Next one in Q2. | Not formally issued. Clean up on site by end Sept. 2nd audit in Oct | Action OSHH/3 and OSHC/1/2 | SP/2001 audit executed by OSHE/C on long distance logistics in Jan | Include 3 audits in 2008
18 |  | Develop and implement Health and Welfare activities and monitor/review quaterly. | Health & Welfare review quaterly report | OSHH | Jim | Number | 4 | 1 | 1 | 1 | 2 | 1 |  | 1 |  | PDO Welfare meeting Kicked Off. Health Surveillance Committee Kicked OFF (TOR agreed plus first meeting held) |  | PDO Welfare meeting in place. Died a bit in June/July. Back on track. |  | Active Health and Welfare committee operating | Continue in 2008
19 |  | Quaterly review of HSE lagging and leading indicators | Quarterly report on indicators below: | Mgmt-TL's | Tony/Kevin | Number | 4 | 1 | 1 | 1 | 2 | 1 |  | 1 |  | This one |  | This one |  | This one
LAGGING INDICATORS
|  |  | Fatalities |  |  | no. | 0 |  | 0 |  | 0 |  |  |  | 0
|  |  | LTIF |  |  | LTIF | 0.5 |  | 0 |  | 0.45 |  |  |  | 0.35 |  |  |  |  | 3 LTI's to date
|  |  | TRCF |  |  | TRCF | 5 |  | 3.52 |  | 5.4 |  |  |  | 5.4 |  |  |  |  | Higher then PDO but our reporting is at a much higher level. | Workside Hazards focus in 2008
|  |  | TROIF |  |  | TROIF | ??? |  | 0 |  | 0.3 |  |  |  | 0.22 |  |  | TROIF is green BUT classification questioned |  | 2 cases reported to date
|  |  | RTAF |  |  | RTAF | 0.9 |  | 1.3 |  | 2.1 |  |  |  | 2.5 |  |  |  |  | Higest risk area: poor performance | DtS Focus in 2008
LEADING INDICATORS :
|  |  | Number of STOP Cards |  | Akhtar | Number | no/month | 100 | 150 | 200 | 495 | 300 |  | 300 | 600 | 206 Stop, 219 NCR's |  |  |  | STOP operating well | Continue focus in 2008
|  |  | Health Awareness Sessions |  | Jim | Number | 20 | 5 | 6 | 5 | 10 | 5 |  | 5 | 5 | Beat the heat: 6 done. HSE Meeting PDO - health reporing, health statistics. Monthly report now includes health stats. |  | Beat the heat & manual lifting done | Diet and exercise in Sept | Numerous sessions at site | Continue in 2008
|  |  | Environmental Awareness Sessions |  | Sabrina | Number | 4 | 1 | 0 | 1 | 2 | 1 |  | 1 | 1 | None formally held. | Action OSHH/2/3 one at site | Held at site by PEC. One e-mail version here at MAF. | Presentation by PEC Env Adv in Oct OSHH/2 to do a coffee-shop display | Presentation environmental completed. Also used as Safety Moment" topic | Continue in 2008
|  |  | PDO staff Driving Safety Forums |  | Zahran | Number | 8 | 2 | 0 | 2 | 0 | 2 |  | 2 | 6 | Outstanding. 1 tried at site - no one showed up. | Action OSHH/3: relaunch at site Action OSHH: one in MAF/Sharjah | None done for PDO staff. Contractor staff: on site being executed. | Action OSHH/3: relaunch at site Action OSHH: one in MAF/Sharjah | Sessions held at site and MAF. Well attended. Safety Moments: 3 Road safety topics per session | Continue in 2008
20 | Audit | Develop PDO Contract HSE audit/inspection/monitoring plan | Approved PDO Contract HSE audit/inspection/monitoring plan: to be issued quaterly as function of project activities. | OSHH | Kevin | Number | 4 | 1 | 1 | 1 | 2 | 1 |  | 1 |  | On site issued and working. Needs to be visible. | Issue May/June in agenda format for all to see (OSHH/3) | On site issued and working. Needs to be visible. | Issue in agenda format for all to see (OSHH/3) | Was shown in coodidor. Working well at site | Intergrated with FSI and QA/QC for 2008
21 |  | Implement PDO Contract HSE audit/inspection/monitoring plan, track audit items and close out recommendations. | Monthly review of: (1) Audit/inspection/montoring activities held against plan (2) Outstanding Action items | Mgmt-TL's | Kevin | Number | 12 | 3 | 2 | 3 | 6 | 3 |  | 3 |  | Monthly review done by OSHH/3 within team. Needs to be more visible. 55% of planned inspections done (joint PEC/PDO/Gal/Tek) |  | Monthly review done by OSHH/3 within team. Needs to be more visible. 75% of planned inspections done (joint PEC/PDO/Gal/Tek) |  | Kept on track and achieved but no formal review done
22 |  | Train 5 personnel to conduct internal audit to the level expected in OHSAS 180001 (EP-04 or equivalent) | Training Matrix/Audit | Mgmt-TL's | Kevin | Number | 5 |  |  |  |  | 2 |  | 3 |  | Not clear how this will be tracked: is this info available from ESS? |  | Training was not identified in SAPHIRE so will not happen in 2008 | Move item to 2008 | These courses were not identified as part of the PDP's. No progress made | Drop. Do not repeat.
23 |  | External verification of HSEMS applied in Harweel | 2 Level 1/2 HSE MS audits | MSE | Ian/Tony | Number | 2 |  |  | 1 Level 1 | 1 |  |  | 1 Level 2 |  | June audit TOR draft available | Level 1 audit in June. Health check in May | HSEMS Audit done | Follow up to be completed. Follow up health check end Nov. | Folow up audit oustanding | Follow up audit in Q1 2008. Cover site only
24 | Management Reviews | Review status of HSE plan implementation | Quarterly report and MOM of the review meeeting | Mgmt-TL's | Tony | Number | 4 | 1 |  | 1 |  | 1 |  | 1 | 1 | this one |  | this one |  | this one
25 |  | SAQ by Management Team | 2 completed SAQ's | Mgmt-TL's | Tony | Number | 2 | 1 | [5 empty] | 1 |  | Outstanding: Tony | Issue SAQ instruction (OSHH end April) | Done as part of the HSEMS audit. In June | Output still to be shared in more detail (OSHH action) | No repeat of SAQ done. | Do one in 2008 and compare wth result of June last year.
26 |  | Review/evaulate 2007 performance as input to 2008 HSE Plan | Review Meeting held | Mgmt-TL's | Ian/Tony | Number | 1 | [6 empty] | 1 | 1 | year end |  |  |  | this one
Author Accepted: Kevin Doyle, Tony van Thiel
Signed off by: OSH, OSHC and OSHH (6/Feb/2008) | Accepted Challenge: MGMT team
Accepted : Project Manager Ian Hill
Note on D2: PHAIGK: This column has been inserted to describe and clarify what is to be measured for some actions.